## All Fixes
BillRaja GST Report Module — Production Fixes
13 issues identified • 9 code fixes applied • 4 verified already handled • 7 files modified
# | Severity | Status | Fix Title | What Was Wrong | What Was Done | Files Changed | Manual Action?
1 | CRITICAL | Fixed | Financial Year Period Missing | Cloud Functions only wrote monthly/quarterly/yearly analytics periods. The FY period (April–March, India standard) was never computed — so the FY tab in the UI had no server-aggregated data and always fell back to an incomplete local list. | Added getIndianFyKey() helper. Extended buildGstPeriods() and buildInputGstPeriods() to emit a 4th financialYear period. writeOwnerAnalytics() now writes 5 new FieldValue.increment fields (intraTaxableAmount, interTaxableAmount, intraCgst, intraSgst, interIgst) for each period doc. | functions/index.js | Deploy functions
2 | HIGH | Fixed | HSN Tax Miscalculation | The HSN tab computed per-item tax from item.total × gstRate, ignoring invoice-level discounts. If an invoice had a 10% discount, HSN totals would be ~10% higher than actual tax collected — a GST compliance risk. | Added discountRatio = inv.taxableAmount / inv.subtotal. Each item's taxable amount is now item.total × discountRatio, so discount is proportionally distributed across line items before tax computation. | lib/screens/gst_report_screen.dart | None
3 | HIGH | Fixed | Raw Errors Leaked to UI | Catch blocks interpolated raw exception messages (e.g., Firestore permission errors, network stack traces) directly into user-visible SnackBars. Unprofessional and a potential info-leak. | Replaced raw error strings with localized s.gstReportLoadError. Added debugPrint(stackTrace) so devs still get diagnostics in the console. | lib/screens/gst_report_screen.dart | None
4 | HIGH | Fixed | PO Team Permission Bypass | Purchase orders were loaded without checking team permissions. A restricted team member (canViewOthersInvoices = false) could see ALL team POs in the Input GST tab and in exports — violating the same permission model enforced on invoices. | Added the same onlyMine guard used for invoices: if the user is a restricted team member, createdByUid is passed to filter POs to only their own. Applied in both _loadPurchaseOrders() and _shareFullReport(). | lib/screens/gst_report_screen.dart lib/services/purchase_order_service.dart | None
5 | HIGH | Fixed | PO Pagination Missing | Purchase orders were loaded all at once with no pagination. For businesses with hundreds of POs per period, this meant a single massive Firestore read — slow, expensive, and could hit Firestore's document-per-query limits. | Added getPurchaseOrdersPage() with cursor-based pagination matching the invoice pattern. Added _poCursor, _hasMorePOs, _isLoadingMorePOs state vars. Added "Load More" button to the Input tab. | lib/screens/gst_report_screen.dart lib/services/purchase_order_service.dart | None
6 | HIGH | Fixed | GSTR-3B Intra/Inter From Local List | The GSTR-3B tab computed intra-state vs inter-state tax breakdown by looping _invoices (local paginated list). For team owners, this missed invoices not yet loaded. For restricted members, it showed only their own data instead of the team total. | Cloud Function now writes intraTaxableAmount, interTaxableAmount, intraCgst, intraSgst, interIgst into each period summary doc. GstPeriodSummary model updated with 5 new fields. _buildGstr3bTab now receives these as parameters (with local fallback when summary is null). | functions/index.js lib/modals/analytics_models.dart lib/screens/gst_report_screen.dart | Deploy functions
7 | HIGH | Fixed | Client-Side PO Filtering | getPurchaseOrders() fetched ALL POs then filtered by status and gstEnabled in Dart. This downloaded unnecessary documents, wasting bandwidth and Firestore reads — especially bad on mobile. | Moved status, gstEnabled, and createdByUid filters into the Firestore query itself (server-side). Added 2 composite indexes to firestore.indexes.json to support the new query patterns. | lib/services/purchase_order_service.dart firestore.indexes.json | Deploy indexes
8 | MEDIUM | Fixed | Team Summary vs List Mismatch | Restricted team members see summary cards with team-wide totals but their invoice/PO list only shows their own. This is confusing — the numbers don't add up and they might think it's a bug. | Added an amber info banner: "Summary totals include all team invoices. The list below shows only your invoices." Rendered only when user is a restricted team member. Translated into all 5 app languages (EN, HI, TA, AS, GU). | lib/screens/gst_report_screen.dart lib/l10n/app_strings.dart lib/l10n/translations/*.dart (5 files) | None
9 | MEDIUM | Fixed | Temp CSV Files Not Cleaned | CSV export created a temp directory via Directory.systemTemp.createTemp() but never deleted it after sharing. Over time, orphaned CSV files accumulate on the device. | Wrapped the SharePlus call in try/finally. The finally block deletes the temp directory recursively. Failure is silently caught to avoid crashing the share flow. | lib/screens/gst_report_screen.dart | None
10 | MEDIUM | Already OK | Unbounded Year Selectors | Year pickers could theoretically allow arbitrary years, causing queries on empty data ranges. | Verified: the period selector already uses hardcoded chips for current year, year-1, and year-2 only. No free-text year input exists. Already bounded by design. | (no changes needed) | None
11 | MEDIUM | Fixed | Increment Drift Detection | FieldValue.increment() can drift over time (retries, partial failures, Cloud Function bugs). If the pre-aggregated summary diverges from actual invoice data, there's no way for users to know the numbers are wrong. | Added drift detection: when the owner has fully loaded all invoices (no more pages) and summary.invoiceCount ≠ loaded count, an orange warning banner appears: "Summary totals may be out of sync." Translated into all 5 languages. | lib/screens/gst_report_screen.dart lib/l10n/app_strings.dart lib/l10n/translations/*.dart (5 files) | None
12 | LOW | Already OK | Export Progress Indicator | No visual feedback during report export, user might tap the button multiple times. | Verified: _isSharingReport flag already disables the button and shows a CircularProgressIndicator while export is in progress. Already implemented. | (no changes needed) | None
13 | LOW | Already OK | Secure Sharing of GST Data | Export/share could potentially include data the user shouldn't see. | Verified: Fix 4's createdByUid permission gating is applied in _shareFullReport() and _loadPurchaseOrders(). Exports are already scoped to the user's permitted data. | (no changes needed) | None

## Manual Steps
Things YOU Need To Do Manually
These cannot be done from code alone — they require Firebase CLI or console access
# | What To Do | Why / Details | Priority
1 | Deploy Cloud Functions | Fixes 1 & 6 added new logic to functions/index.js — the financialYear period and intra/inter GSTR-3B fields. Without deploying, the old function runs and new summary fields stay zero. Run: cd functions && npm run deploy | CRITICAL
2 | Deploy Firestore Indexes | Fix 7 added 2 composite indexes to firestore.indexes.json for PO queries with server-side filtering. Without these, the new Firestore queries will fail with a "requires an index" error. Run: firebase deploy --only firestore:indexes | CRITICAL
3 | Backfill FY Analytics (Optional) | New FY period summaries only populate for NEW invoice writes after deployment. Old invoices won't have FY data. To backfill, you can write a one-time Cloud Function or script that reads all existing invoices and re-triggers the analytics pipeline. Without this, FY tab uses local fallback until enough new activity accumulates. | RECOMMENDED
4 | Run flutter analyze locally | Flutter SDK was not available in the sandbox. Run `flutter analyze` in your local environment to confirm zero warnings/errors before merging. | REQUIRED
5 | Test on a real device | Verify: (1) PO pagination "Load More" works, (2) GSTR-3B intra/inter numbers match manual calculation, (3) team member info banner appears correctly, (4) drift warning shows when expected, (5) CSV temp files are cleaned up. | REQUIRED

## Files Modified
Files Modified Across All Fixes
# | File Path | What Changed | Fixes Involved
1 | functions/index.js | Added getIndianFyKey(), financialYear period to buildGstPeriods() & buildInputGstPeriods(), 5 new FieldValue.increment fields for intra/inter breakdown in writeOwnerAnalytics() | 1, 6
2 | lib/modals/analytics_models.dart | 5 new fields on GstPeriodSummary (intraTaxableAmount, interTaxableAmount, intraCgst, intraSgst, interIgst) + fromMap() deserialization | 6
3 | lib/screens/gst_report_screen.dart | HSN discount ratio, error message cleanup, PO permission gating, PO pagination, GSTR-3B summary params, team note banner, drift detection banner, CSV cleanup | 2,3,4,5,6,8,9,11
4 | lib/services/purchase_order_service.dart | New getPurchaseOrdersPage() method, server-side filtering for status/gstEnabled/createdByUid, removed client-side where() filters | 4, 5, 7
5 | firestore.indexes.json | 2 new composite indexes for PO queries (status+gstEnabled+createdAt, status+gstEnabled+createdByUid+createdAt) | 7
6 | lib/l10n/app_strings.dart | 2 new getter strings: gstReportTeamSummaryNote, gstReportDriftWarning | 8, 11
7 | lib/l10n/translations/en.dart | English translations for team note + drift warning | 8, 11
8 | lib/l10n/translations/hi.dart | Hindi translations | 8, 11
9 | lib/l10n/translations/ta.dart | Tamil translations | 8, 11
10 | lib/l10n/translations/as.dart | Assamese translations | 8, 11
11 | lib/l10n/translations/gu.dart | Gujarati translations | 8, 11